## Tasks
AT RISK | PROJECT | OWNER | TASK | STORY POINTS | START | FINISH | PERCENT | DURATION in days | STATUS | COMMENTS
| CUSTOMER PORTAL | Sarah | Requeirements gathering |  | 2026-02-03 | 2026-02-05 | 100% | 3 | Completed
| CUSTOMER PORTAL | Sarah | Database structure |  | 2026-02-06 | 2026-02-11 | 100% | 4 | Completed
| CUSTOMER PORTAL | Ethan | Authentication module |  | 2026-02-12 | 2026-02-20 | 100% | 7 | Completed
| CUSTOMER PORTAL | Ethan | Dashboard development |  | 2026-02-23 | 2026-03-04 | 75% | 8 | On hold | Dashboard charts under development
✓ | CUSTOMER PORTAL | Sophia | User acceptance testing | Stakeholder availability | 2026-03-05 | 2026-03-11 | 30% | 5 | On hold | Waiting for stakeholder feedback
| INVENTORY SYSTEM | Noah | Requeirements gathering |  | 2026-02-10 | 2026-02-11 | 100% | 2 | Completed
| INVENTORY SYSTEM | Noah | Data model |  | 2026-02-12 | 2026-02-17 | 100% | 4 | Completed
| INVENTORY SYSTEM | Emma | Automation scripts |  | 2026-02-18 | 2026-02-27 | 90% | 8 | On hold | Final validation pending
✓ | INVENTORY SYSTEM | Emma | Integration testing | Dependency on external systems | 2026-03-02 | 2026-03-06 | 40% | 5 | On hold | Integration issue identified
| ANALYTICS DASHBOARD | Liam | KPI definition |  | 2026-02-16 | 2026-02-18 | 100% | 3 | Completed
| ANALYTICS DASHBOARD | Liam | Data preparation |  | 2026-02-19 | 2026-02-25 | 100% | 5 | Completed
| ANALYTICS DASHBOARD | Ana | Dashboard layout |  | 2026-02-26 | 2026-03-04 | 80% | 5 | On hold | Final layout adjustments
| ANALYTICS DASHBOARD | Ana | Performace indicators |  | 2026-03-05 | 2026-03-16 | 20% | 8 | On hold | Initial development
Formulas:
DURATION in days = IF(AND(ISNUMBER([START]), ISNUMBER([FINISH])), NETWORKDAYS([START], [FINISH]), IF(ISNUMBER([START]), NETWORKDAYS([START], TODAY()), ""))

## Timeline
Start: | 2026-02-01 | PROJECT | TASK | STATUS | 31/01/2026 | 2026-01-02 | 2026-02-02 | 2026-03-02 | 2026-04-02 | 2026-05-02 | 2026-06-02 | 2026-07-02 | 2026-08-02 | 2026-09-02 | 2026-10-02 | 2026-11-02 | 2026-12-02 | 13/02/2026 | 14/02/2026 | 15/02/2026 | 16/02/2026 | 17/02/2026 | 18/02/2026 | 19/02/2026 | 20/02/2026 | 21/02/2026 | 22/02/2026 | 23/02/2026 | 24/02/2026 | 25/02/2026 | 26/02/2026 | 27/02/2026 | 28/02/2026 | 2026-01-03 | 2026-02-03 | 2026-03-03 | 2026-04-03 | 2026-05-03 | 2026-06-03 | 2026-07-03 | 2026-08-03 | 2026-09-03 | 2026-10-03 | 2026-11-03 | 2026-12-03 | 13/03/2026 | 14/03/2026 | 15/03/2026 | 16/03/2026 | 17/03/2026 | 18/03/2026 | 19/03/2026 | 20/03/2026 | 21/03/2026 | 22/03/2026 | 23/03/2026 | 24/03/2026 | 25/03/2026 | 26/03/2026 | 27/03/2026 | 28/03/2026 | 29/03/2026 | 30/03/2026 | 31/03/2026
End: | 2026-04-01 | CUSTOMER PORTAL | Requeirements gathering | completed | bar: 2026-01-02 to 2026-12-02
|  | CUSTOMER PORTAL | Database structure | completed | bar: 2026-01-02 to 2026-12-02
|  | CUSTOMER PORTAL | Authentication module | completed | [13 empty] | █ | █ | █ | █ | █ | █ | █ | bar: 2026-01-02 to 2026-12-02
|  | CUSTOMER PORTAL | Dashboard development | on hold | [22 empty] | █ | █ | █ | █ | █ | █ | █ | █ | █ | █
|  | CUSTOMER PORTAL | User acceptance testing | on hold | [32 empty] | █ | █ | █ | █ | █ | █ | █
|  | INVENTORY SYSTEM | Requeirements gathering | completed | bar: 2026-01-02 to 2026-12-02
|  | INVENTORY SYSTEM | Data model | completed | [13 empty] | █ | █ | █ | █ | bar: 2026-01-02 to 2026-12-02
|  | INVENTORY SYSTEM | Automation scripts | on hold | [17 empty] | █ | █ | █ | █ | █ | █ | █ | █ | █ | █
|  | INVENTORY SYSTEM | Integration testing | on hold | [29 empty] | █ | █ | █ | █ | █
|  | ANALYTICS DASHBOARD | KPI definition | completed | [15 empty] | █ | █ | █
|  | ANALYTICS DASHBOARD | Data preparation | completed | [18 empty] | █ | █ | █ | █ | █ | █ | █
|  | ANALYTICS DASHBOARD | Dashboard layout | on hold | [25 empty] | █ | █ | █ | █ | █ | █ | █
|  | ANALYTICS DASHBOARD | Performace indicators | on hold | [32 empty] | █ | █ | █ | █ | █ | █ | █ | █ | █ | █ | █ | █
Update

## Guideline
PROJECT MANAGEMENT SYSTEM
Excel + Office Script
A lightweight project management system built entirely in Microsoft Excel
Designed to provide a simple and visual way to organize projects, track tasks, monitor deadlines, identify risks, and visualize project timelines — without requiring additional project management software.
01 - GETTING STARTED
The system is organized into two main areas:
TASKS
The main workspace where project information is entered and managed.
TIMELINE
An automatically generated visual timeline based on the information entered in the Tasks worksheet.
You only need to maintain your project information in the Tasks worksheet. The Timeline is generated automatically by the Office Script.
02 - TASKS
Each row represents one task within a project.
FIELD | DESCRIPTION
AT RISK | Indicates whether the task requires attention due to an identified risk.
PROJECT | Name of the project associated with the task.
OWNER | Person responsible for the task.
TASK | Activity or deliverable that needs to be completed.
RISK | Description of a potential issue, dependency, or condition that may affect the task.
START | Planned start date.
FINISH | Planned completion date.
PERCENT COMPLETE | Current completion percentage of the task.
DURATION (days) | Number of days planned for the task.
STATUS | Current task status.
COMMENTS | Additional information, notes, decisions, or updates.
03 - STATUS
Use one of the following status values:
NOT STARTED
The task has not started yet.
IN PROGRESS
The task is currently being worked on.
ON HOLD
The task has been temporarily paused.
COMPLETED
The task has been completed.
Using standardized status values is important because the Timeline uses them to determine the visual representation of each task.
04 - PROJECT COLORS
Projects are automatically identified using pastel colors.
Each project receives its own visual color, making it easier to distinguish multiple projects within the Timeline.
You do not need to manually configure a color when creating a new project.
Simply enter the project name in the PROJECT column.
The system will automatically assign its visual identity.
PROJECT A → Pastel Blue
PROJECT B → Pastel Purple
PROJECT C → Pastel Green
PROJECT D → Pastel Yellow
PROJECT E → Pastel Pink
The pastel palette was intentionally selected to keep the interface clean, readable, and suitable for professional environments.
05 - TIMELINE
The Timeline provides a visual representation of your project schedule.
To generate the Timeline:
1. Enter the desired start date.
2. Enter the desired end date.
3. Run the Timeline Office Script.
The system will automatically:
→ Read the selected date range
→ Identify tasks within the period
→ Organize tasks by project
→ Apply project colors
→ Apply status colors
→ Draw the task duration
→ Highlight the current date
Only tasks that overlap with the selected date range will appear in the Timeline.
06 - READING THE TIMELINE
The left side of the Timeline displays:
PROJECT
TASK
STATUS
The remaining columns represent calendar dates.
A colored bar indicates the period associated with each task.
STATUS COLORS
Green — Completed
Blue — In Progress
Yellow — On Hold
Gray — Not Started
The current date is highlighted separately to make it easier to understand the project's position in time.
07 — ADDING A NEW PROJECT
No configuration is required.
Create your project directly in the Tasks worksheet:
PROJECT
WEBSITE REDESIGN
Then add the associated tasks:
Requirements
UX Design
Development
Testing
Deployment
The next time the Timeline script runs, the new project will automatically be included and assigned a pastel color.
08 — ADDING A NEW TASK
Create a new row in the Tasks worksheet and complete the required information.
After updating the table, run the Timeline script again.
The Timeline will automatically reflect the new information.
09 — RISK MANAGEMENT
The RISK field can be used to document anything that may affect the successful completion of a task.
Examples include:
Dependency on stakeholder approval
External system availability
Requirements may change
Limited resource availability
Data quality issues
No significant risk identified
The purpose of this field is not to calculate task effort. It provides context about potential problems that should be monitored during project execution.
10 — RECOMMENDED WORKFLOW
PLAN
Create the project and define its tasks.
↓
ASSIGN
Define an owner for each activity.
↓
ASSESS
Identify risks and dependencies.
↓
SCHEDULE
Define start and finish dates.
↓
EXECUTE
Update progress and status as work progresses.
↓
MONITOR
Use the Timeline to visualize deadlines and project progress.
↓
COMPLETE
Mark finished activities as Completed.
11 — IMPORTANT
For the automation to work correctly:
Do not rename the required columns used by the Office Script.
Keep status values consistent.
Use valid Excel dates for START and FINISH.
Do not manually modify the generated Timeline unless necessary.
Update project information in the Tasks worksheet and regenerate the Timeline instead.
12 — BUILT WITH
Microsoft Excel
Office Scripts
TypeScript
No VBA is required.
13 — PROJECT PURPOSE
This project was created as a lightweight alternative for managing multiple projects directly inside Excel.
The goal is not to reproduce every feature of dedicated project management platforms, but to provide a practical system for teams and individuals who already work extensively with Microsoft Excel.
The system focuses on:
Simplicity · Visibility · Automation · Risk Awareness · Project Tracking
CLEAN DATA. CLEAR PROJECTS. BETTER VISIBILITY.